## Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Account Management |  | 41 | 41 | 0 |  |  |  |  | 100% | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7
1.1 | Home Page | Diana | 3 | 3 | 0 | 1 | 2024-04-04 | 2024-04-08 | 3 | 100%: 100%
1.1.1 | Registration (Users) | Elisa | 5 | 5 | 0 | 1 | 2024-04-08 | 2024-04-10 | 3 | 100%: 100%
1.2 | Registration (Nutritionists) | Lorenzo M. | 5 | 5 | 0 | 1 | 2024-04-08 | 2024-04-10 | 3 | 100%: 100%
1.3 | Insertion of certificate (Nutritionists) | Lorenzo M. | 8 | 8 | 0 | 1 | 2024-04-10 | 2024-04-12 | 3 | 100%: 100%
1.4 | Login for Users (Nutritionists) | Elisa | 6 | 6 | 0 | 1 | 2024-04-15 | 2024-04-17 | 3 | 100%: 100%
1.5 | Logout for Users (Nutritionists) | Lorenzo M. | 6 | 6 | 0 | 1 | 2024-04-18 | 2024-04-19 | 2 | 100%: 100%
1.6 | Changing information into MyProfile page (Users and Nutritionists) | Elisa | 8 | 8 | 0 | 1 | 2024-04-22 | 2024-04-24 | 3 | 100%: 100%
2 | Booking and chat |  | 66 | 66 | 0 |  |  |  |  | 100%: 100%
2.1 | Search nutritionists (Users) | Diana | 10 | 10 | 0 | 2 | 2024-04-26 | 2024-04-30 | 3 | 100%: 100%
2.2 | Contact nutritionists (Users) | Lorenzo F. | 15 | 15 | 0 | 2 | 2024-04-26 | 2024-04-30 | 3 | 100%: 100%
2.3 | Chat for Nutritionists (Users) | Lorenzo F. | 15 | 15 | 0 | 2 | 2024-05-02 | 2024-05-06 | 3 | 100%: 100%
2.4 | Booking an appointment (Users) | Lorenzo M. | 10 | 10 | 0 | 2 | 2024-05-03 | 2024-05-06 | 2 | 100%: 100%
2.5 | View appointments (Users and Nutritionists) | Lorenzo M. | 8 | 8 | 0 | 2 | 2024-05-07 | 2024-05-08 | 2 | 100%: 100%
2.6 | List of patients (Nutritionists) | Elisa | 8 | 8 | 0 | 2 | 2024-05-09 | 2024-05-10 | 2 | 100%: 100%
3 | FoodPlan and recipes |  | 36 | 36 | 0 |  |  |  |  | 100%: 100%
3.1 | List of ingredients in DB | Diana | 10 | 10 | 0 | 3 | 2024-05-13 | 2024-05-15 | 3 | 100%: 100%
3.2 | Creation of a new FoodPlan (Nutritionists) | Diana | 10 | 10 | 0 | 3 | 2024-05-16 | 2024-05-20 | 3 | 100%: 100%
3.3 | View of a FoodPlan (Users) | Lorenzo F. | 8 | 8 | 0 | 3 | 2024-05-21 | 2024-05-22 | 2 | 100%: 100%
3.4 | API for recipes | Diana | 8 | 8 | 0 | 3 | 2024-05-21 | 2024-05-23 | 3 | 100%: 100%
4 | Progress |  | 21 | 21 | 0 |  |  |  |  | 100%: 100%
4.1 | Create progress history (Nutritionists) | Lorenzo M. | 12 | 12 | 0 | 4 | 2024-05-24 | 2024-05-28 | 3 | 100%: 100%
4.2 | View of progress (Users) | Lorenzo M. | 9 | 9 | 0 | 4 | 2024-05-29 | 2024-05-30 | 2 | 100%: 100%
5 | Reviews |  | 16 | 16 | 0 |  |  |  |  | 100%: 100%
5.1 | View a review (Users and Nutritionists) | Lorenzo M. | 6 | 6 | 0 | 5 | 2024-05-29 | 2024-05-29 | 1 | 100%: 100%
5.2 | Create a new review (Users) | Lorenzo M. | 10 | 10 | 0 | 5 | 2024-05-29 | 2024-05-29 | 1 | 100%: 100%
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 180 | 180 | 0 | 50 | 3.6 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 180 | 176.4 | 172.8 | 169.2 | 165.6 | 162 | 158.4 | 154.8 | 151.2 | 147.6 | 144 | 140.4 | 136.8 | 133.2 | 129.6 | 126 | 122.4 | 118.8 | 115.2 | 111.6 | 108 | 104.4 | 100.8 | 97.2 | 93.6 | 90 | 86.4 | 82.8 | 79.2 | 75.6 | 72 | 68.4 | 64.8 | 61.2 | 57.6 | 54 | 50.4 | 46.8 | 43.2 | 39.6 | 36 | 32.4 | 28.8 | 25.2 | 21.6 | 18 | 14.4 | 10.8 | 7.2 | 3.6
[10 empty] | ESTIMATE | 180 | 180 | 180 | 180 | 179 | 178 | 173 | 169 | 165 | 163 | 159 | 157 | 155 | 153 | 150 | 147 | 144 | 141 | 139 | 139 | 130 | 121 | 114 | 114 | 109 | 99 | 89 | 85 | 81 | 77 | 73 | 69 | 65 | 63 | 59 | 55 | 53 | 47 | 39 | 37 | 33 | 29 | 25 | 20 | 16 | 13 | 10 | 6 | 2 | 0
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 0 | 0 | 0 | 1 | 1 | 5 | 4 | 4 | 2 | 4 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 0 | 9 | 9 | 7 | 0 | 5 | 10 | 10 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | 2 | 6 | 8 | 2 | 4 | 4 | 4 | 5 | 4 | 3 | 3 | 4 | 4 | 2 | 0
[10 empty] | HRS REMAINING | 180 | 180 | 180 | 179 | 178 | 173 | 169 | 165 | 163 | 159 | 157 | 155 | 153 | 150 | 147 | 144 | 141 | 139 | 139 | 130 | 121 | 114 | 114 | 109 | 99 | 89 | 85 | 81 | 77 | 73 | 69 | 65 | 63 | 59 | 55 | 53 | 47 | 39 | 37 | 33 | 29 | 25 | 20 | 16 | 13 | 10 | 6 | 2 | 0 | 0
CLICK HERE TO CREATE GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
High | 1 | Registration, login, profile update, nutritionist certification upload, log out. | Account management | This sprint implements the main functionalities of an account both for normal users and nutritionist, such as registration, log in, log out, profile update, nutritionist certificate upload. | Lorenzo M. and Elisa | 41 | Completed | This sprint is the initial phase of the application, where we managed the correct working of the website. | Not Started | 41
High | 2 | Booking an appointment and contact through a chat between nutritionist and patient. | Booking and chat | This sprint implements the possibility for a logged user to search for nutritionists in a specific city, to contact one of the found nutritionists through a private chat or to check directly the available days and slots in order to book an appointment with him/her for a check-up. The normal users also can see a history of all their bookings. From the nutritionist point of view, they can read and answer the messages received in the private chat, they can check their own agenda and the list of their patients. | Lorenzo M. and Lorenzo F. | 66 | Completed | In this sprint we allow logged users to book an appointment. | In Progress | 66
High | 3 | Creation and visualization of a personalized foodplan, together with a library of receipes. | Foodplan and receipes | This sprint implements the core functionality of the application, which is the possibility of nutritionists to create personalized foodplans for their patients, by choosing ingredients from a rich database and their associated quantities for each meal of each day of the week. They can also check the daily nutritional values of what is currently added to the plan. The patients instead can visualize their current foodplan and also search for recipes by typing the ingredients of their foodplan. | Diana and Lorenzo F. | 36 | Completed | The main functionality of displaying the foodplans is implement during this sprint. | Completed | 36
Medium | 4 | Update and visualization of a patient's progress. | Progress | This sprint implements the management part of users progress, so a nutritionist can add the measurements of a patient and also patients have a chart to see their own progress. | Elisa and Lorenzo M. | 21 | Completed | During this sprint we want to display the progress over time of the users. |  | 21
Low | 5 | Insertion and visualization of reviews. | Reviews | This sprint implements the insertion and the visualization of reviews and ratings that a user can write about a nutritionist. | Diana and Lorenzo M. | 16 | Completed | We added the possibility to review the nutritionist. |  | 16

## Product Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
Product Backlog
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | ADDED BY | DATED ADDED
High | 1 | Account management | Home Page | Display the landing page of the web application and the navigation hub that allows visitors to navigate though the website. We deploy two containers for the front-end using React and three containers for the backend using NodeJS. | Diana | 2024-04-05
High | 1 | Account management | Registration (Users) | Adding to the React component users registration handled by the backend in NodeJS and the communication with a MongoDB permanent storage. | Elisa | 2024-04-09
High | 1 | Account management | Registration (Nutritionists) | Adding to the React component the nutritionists registration handled by the backend in NodeJS and the communication with a MongoDB permanent storage. | Lorenzo M. | 2024-04-10
Medium | 1 | Account management | Insertion of certificate (Nutritionists) | The management both in frontend and in backend of pdf files storing the certification that a nutritionist must provide to be enabled on the application. | Lorenzo M. | 2024-04-12
High | 1 | Account management | Login (Users and Nutritionists) | Implementation of login made by a react component and the backend logic made with session storage. | Elisa | 2024-04-13
High | 1 | Account management | Logout (Users and Nutritionists) | Logout button, and logic implementation both in frontend and in backend. | Lorenzo M. | 2024-04-13
Low | 1 | Account management | Changing information into MyProfile page | The creation of a React page to modify the user informations and the implementation of APIs to the backend to manage edits also in database. | Elisa | 2024-04-15
High | 2 | Booking and chat | Search nutritionists (Users) | Creation of a React page to search nutritionists by location and also the implementation of the APIs in nodejs to perform the research in the DB. | Diana | 2024-04-18
High | 2 | Booking and chat | Contact nutritionists (Users) | Add of a button in the nutritionist page and a popup to send messages and contact a nutritionist. | Lorenzo F. | 2024-04-19
High | 2 | Booking and chat | Chat (Nutritionists and Users) | The implementation of a react Component for the chat, also the logic behind the application, the display of messages | Lorenzo F. | 2024-04-20
High | 2 | Booking and chat | Booking an appointment (Users) | Implementation of the possibility for users to book an appointment with a specific nutritionist, allowing them to choose among the free spots. The bookings are saved in the MongoDB data storage. | Lorenzo M. | 2024-05-03
Medium | 2 | Booking and chat | View appointments (Users and Nutritionists) | Allowing the Users and the Nutritionists to see their appointments by retrieving them from the MongoDB collection. | Lorenzo M. | 2024-04-24
Medium | 3 | Booking and chat | List of patients (Nutritionists) | Display the informations of the nutritionists' patients, by listing them in the profile section. | Elisa | 2024-04-25
High | 3 | Foodplan and receipes | List of ingredients in DB | Adding in the MongoDB datastorage a precise list of ingredients with their relative section. | Diana | 2024-04-25
High | 3 | Foodplan and receipes | Creation of a new FoodPlan (Nutritionists) | Nutritionist can create personalized foodplans for their clients, specifying the food and the quantity through the communication between React frontend, NodeJS backend and with a pre defined list of foods saved in the MongoDB storage. The foodplan is save in a MongoDB collection. | Diana | 2024-04-27
High | 3 | Foodplan and receipes | View of a FoodPlan (Users) | Users that have already done the first visit can see the foodplan created by their nutritionist, retrieving it from the MongoDB collection. | Lorenzo F. | 2024-04-30
High | 3 | Foodplan and receipes | API for recipes | Users and Nutritionists can search for recipes by typing the food and optionally the quantity. The API call is handled by the communication between the Edamame end point and the React containers. | Diana | 2024-05-02
Medium | 4 | Progress | Create progress history (Nutritionists) | Allowing Nutritionists to add the measurements of a past visit, which are then saved in a MongoDB collection. | Lorenzo M. | 2024-05-02
Medium | 4 | Progress | View of progress (Users) | Displaying charts that describe the progress over time of the users by taking the measurements saved in the MongoDB collection. | Lorenzo M. | 2024-05-06
Low | 5 | Reviews | Allow Users to add a review (Nutritionists) | Logged users can write a review about a specific nutritionist, which is saved in a MongoDB collection. | Lorenzo M. | 2024-05-09
Low | 5 | Reviews | View a review (Users and Nutritionists) | When visiting the page of a nutritionist, the visitor can see all the reviews about him retrieving them from the MongoDB collection. | Lorenzo M. | 2024-05-15