## User Stories
EPIC | USER STORY | PRIORITY | VALUE | RISK | ESTIMATE | RELEASE | ACCEPTANCE
HOME | As a website visitor, I want to read informations about the services, so that I can have an overview of what I can do. | 2 Med | 2 Med | 4 Low | 1 | 1.x | After running the app, the visitor reads informations and services on the homepage.
| As a website visitor, I want to be able to register as a normal user, so that I can have a personalized experience. | 2 Med | 1 High | 2 Med | 2 | 1.x | The visitor registers as a normal user/client by accessing the sign up page and filling the form and a new account is created.
| As a website visitor, I want to be able to register as a nutritionist, so that I cand have a personalized platform. | 2 Med | 1 High | 2 Med | 2 | 1.x | The visitor registers as a nutritionist by accessing the sign up page and by checking the nutritionist checkbox and a new account is created.
| As a nutritionist, I want to be able to upload my certification, so that I can be authorized as a certified nutritionist. | 3 Med | 2 Med | 3 Med | 1 | 1.x | The nutritionist, upon registration, uploads a file in the form.
| As a user, I want to be albe to login, so that I can see my personal informations. | 1 High | 1 High | 1 High | 2 | 1.x | A user (either client or nutritionist) logs in by inserting the correct email and password in the log in form and he/she is redirected to his/her personal area.
| As a user, I want to be albe to logout, so that I can end my session. | 2 Med | 2 Med | 1 High | 1 | 1.x | A user logs out from his/her account through a button in the navbar.
| As a user, I want to be able to edit my profile, so that I can customize informations about me. | 3 Med | 3 Med | 3 Med | 2 | 1.x | A user updates some fields in his/her personal profile and he/she those informations are updated.
APPOINTMENTS | As a client, I want to be able to search for a nutritionist, so that I can find the ones near me. | 2 Med | 1 High | 3 Med | 3 | 1.x | A client selects though a search bar a city and the nutritionists located in that city are displayed.
| As a client, I want to be able to contact a nutritionist, so that I can ask him/her more informations. | 1 High | 1 High | 2 Med | 3 | 2.x | A client starts a chat with a nutritionist where he /she type messages.
| As a nutritionist, I want to be able to chat with a patient, so that I can answer to his/her questions. | 1 High | 1 High | 2 Med | 3 | 2.x | A nutritionist reads the message in the chat and types an answer to it.
| As a client, I want to be able to see the available slots of a nutritionist, so that I can choose one among them for booking. | 2 Med | 2 Med | 2 Med | 1 | 1.x | A client sees on the page of the nutritionist a calendar with the available days and slots.
| As a client, I want to be able to book an appointment with a nutritionist, so that I can schedule a consultation without having to make a phone call or send an email. | 1 High | 1 High | 1 High | 3 | 2.x | A client, once chosen a day and a slot among the available ones, books an appointment for that slot and receives a confirmation.
| As a client, I want to be able to see my bookings, so that I can have a history of all my consultations. | 2 Med | 2 Med | 4 Low | 2 | 2.x | A client reads all his/her bookings, listed in a page of his/her personal area.
| As a nutritionist, I want to be able to see my agenda, so that I can see all the appointments with my patients. | 2 Med | 1 High | 3 Med | 2 | 2.x | A nutritionist sees a calendar filled with his/her appointments.
| As a nutritionist, I want to be able to see my patients, so that I can keep track of them. | 3 Med | 2 Med | 4 Low | 2 | 2.x | A nutritionist sees a list of his/her patients in a page of his/her personal area.
FOODPLAN | As a nutritionist, I want to be able to create a foodplan for a specific patient, so that I can schedule his/her meals. | 1 High | 1 High | 1 High | 3 | 2.x | A nutritionist has a schedule, for meal of each day of the week, where he/she inserts ingredients and associated quantities.
| As a nutritionist, I want to be able to search for a specific ingredient, so that I can insert it in the foodplan with an associated quantity. | 1 High | 1 High | 2 Med | 3 | 2.x | A nutritionist, while creating a foodplan, has a plus button that allows to search through a search bar for a new ingredient to be added to the plan, for a specific meal of a specific day.
| As a nutritionist, I want to be able to see the current nutritional values of the meals while creating a foodplan, so that I can add/remove ingredients. | 2 Med | 2 Med | 3 Med | 2 | 3.x | A nutritionist displays a table where the nutritional values of the ingredients currently inserted in the foodplan for that thay are listed.
| As a client, I want to be able to access my current foodplan, so that I can understand what I should eat and how much. | 1 High | 1 High | 1 High | 3 | 2.x | A client sees the whole foodplan, scheduled by days and by meals, each one containing the associated ingredients and quantities.
| As a client, I want to be able to search for recipes, so that I can vary meals depending on the ingredients of my foodplan. | 2 Med | 2 Med | 2 Med | 3 | 3.x | A client types in a search bar some ingredients and a list of receipes containing those ingredients is displayed.
PROGRESS | As a client, I want to be able to see my progress, so that I can see my changes in time about weight, body fat, body cm. | 2 Med | 2 Med | 3 Med | 1 | 3.x | A client sees his/her personal progress in a page where the history of his/her weight, body fat, body centimeters are recorded.
| As a nutritionist, I want to be able to update the progress of a patient, so that I can keep his/her informations up to date. | 1 High | 1 High | 2 Med | 2 | 3.x | A nutritionist inserts in a sort of form the weight, body fat and body centimeters of the patient in order to update his/her progress.
REVIEWS | As a client, I want to be able to see the reviews about a nutritionist, so that I can read other people's experience with him/her. | 3 Med | 2 Med | 4 Low | 1 | 3.x | A client sees a list of the reviews given by other people to a specific nutritionist.
| As a client, I want to be able to leave a review about a nutritionist, so that I can describe my experience with him/her. | 2 Med | 2 Med | 3 Med | 2 | 3.x | A client inserts a review in a text field and selects a rating for a specific nutritionist and this new review is displayed.
| As a nutritionist, I want to be able to read the reviews about me, so that I can see my patients' opinion. | 3 Med | 3 Med | 4 Low | 1 | 3.x | A nutritionist sees the reviews given to him/her by his/her patients.